## Data Job Costing Tracker KeyFor
| Key Forecasts |  | CONSTRUCTION COMPANY ABC
| info@keyforecasts.com |  | JOB COSTING REPORT
| Phone: 213-444-2224 |  | January 1 - May 30, 2026
Date | Category | Description | Vendor/Employee | Budgeted | Actual | Variance | Metric | Results | Progress Bar | Estimate Used
2026-02-10 | Materials | Copper Piping | Home Depot | 1500 | 1450 | 50 | Total Contract Price | 75000 |  | 92.13%
2026-02-11 | Labor | Lead Tech (10 hrs) | John Doe | 500 | 500 | 0 | Total Estimated Costs | 74528
2026-02-12 | Subcontract | Electrical Rough-in | Sparky LLC | 2500 | 1800 | 700 | Total Actual Costs | 68660
2026-01-05 | Permits | City Building Permit | City of Los Angeles | 850 | 850 | 0 | Gross Profit (Actual) | 6340
2026-01-05 | Permits | Environmental Impact Fee | CA Dept of Revenue | 300 | 315 | -15 | Net Profit Margin % | 8.453%
2026-01-06 | Materials | Rough-in Copper Piping | Ferguson Plumbing | 2200 | 1450 | 750
2026-01-06 | Labor | Demo Crew (16 hrs) | Labor Ready | 640 | 640 | 0
2026-01-07 | Materials | PVC Pipe & Fittings | Home Depot | 450 | 485 | -35
2026-01-08 | Labor | Lead Tech - Demo | John Doe | 550 | 550 | 0
2026-01-09 | Materials | HVAC Ducting - Main | Lennox | 3500 | 3200 | 300
2026-01-10 | Equipment | Scissor Lift Rental | Sunbelt Rentals | 1500 | 1450 | 50
2026-01-11 | Materials | Insulation Rolls | Lowe's | 800 | 725 | 75
2026-01-12 | Labor | HVAC Tech - Rough-in | Robert Smith | 1200 | 1350 | -150
2026-01-13 | Subcontract | Electrical Sub - Panel | Sparky LLC | 2500 | 2500 | 0
2026-01-14 | Materials | Smart Thermostats (5) | Nest/Google | 1500 | 1300 | 200
2026-01-15 | Labor | Helper - Rough-in | Jane Doe | 500 | 480 | 20
2026-01-16 | Materials | Flex Ducting | Ferguson HVAC | 690 | 650 | 40
2026-01-17 | Materials | Braided Supply Lines | Home Depot | 150 | 185 | -35
2026-01-18 | Labor | Plumbing Tech | Mike Ross | 950 | 950 | 0
2026-01-19 | Equipment | Concrete Saw Rental | United Rentals | 350 | 350 | 0
2026-01-20 | Subcontract | Drywall Patching | Drywall Pros | 2500 | 2100 | 400
2026-01-21 | Materials | HVAC Grilles/Vents | Lennox | 400 | 380 | 20
2026-01-22 | Materials | PEX Tubing Rolls | Ferguson Plumbing | 1300 | 1150 | 150
2026-01-23 | Labor | Lead Tech - Install | John Doe | 800 | 800 | 0
2026-01-24 | Materials | Refrigerant Gas | Lennox | 700 | 600 | 100
2026-01-25 | Labor | Tech Assistant | Jane Doe | 359 | 350 | 9
2026-01-26 | Materials | Drain Pans | Ferguson HVAC | 315 | 215 | 100
2026-01-27 | Permits | Final Inspection Fee | City of Los Angeles | 250 | 250 | 0
2026-01-28 | Materials | Electrical Wire 12/2 | Home Depot | 600 | 450 | 150
2026-01-29 | Labor | Lead Tech - Final | John Doe | 850 | 750 | 100
2026-01-30 | Materials | Cleaning Supplies | Lowe's | 100 | 125 | -25
2026-01-31 | Subcontract | Site Cleanup | Junk King | 500 | 500 | 0
2026-02-01 | Materials | Copper Elbows/Tees | Ferguson Plumbing | 467 | 340 | 127
2026-02-02 | Labor | Apprentice Labor | Sam Lee | 355 | 300 | 55
2026-02-03 | Materials | Condenser Brackets | Lennox | 150 | 175 | -25
2026-02-04 | Equipment | Generator Rental | Sunbelt Rentals | 349 | 250 | 99
2026-02-05 | Materials | Sealing Foam | Home Depot | 80 | 110 | -30
2026-02-06 | Labor | Lead Tech | John Doe | 654 | 550 | 104
2026-02-07 | Materials | Plumbing Valves | Ferguson Plumbing | 600 | 650 | -50
2026-02-08 | Materials | Air Filters | Lennox | 200 | 200 | 0
2026-02-09 | Subcontract | Insulation Spray | EcoFoam | 5300 | 3200 | 2100
2026-02-10 | Materials | PVC Cement/Primer | Lowe's | 45 | 60 | -15
2026-02-11 | Labor | Finishing Crew | Labor Ready | 1000 | 950 | 50
2026-02-12 | Materials | Sheet Metal Screws | Home Depot | 50 | 75 | -25
2026-02-13 | Labor | Plumbing Tech | Mike Ross | 950 | 950 | 0
2026-02-14 | Materials | Mastic Sealant | Ferguson HVAC | 120 | 140 | -20
2026-02-15 | Equipment | Trash Bin Rental | Waste Management | 650 | 650 | 0
2026-02-16 | Materials | Electrical Boxes | Home Depot | 100 | 120 | -20
2026-02-17 | Labor | HVAC Tech | Robert Smith | 800 | 800 | 0
2026-02-18 | Materials | Water Heater Unit | Rheem | 2200 | 2050 | 150
2026-02-19 | Labor | Lead Tech | John Doe | 600 | 600 | 0
2026-02-20 | Materials | Gas Piping | Ferguson Plumbing | 400 | 460 | -60
2026-02-21 | Subcontract | Structural Engineer | SE Consulting | 1500 | 1500 | 0
2026-02-22 | Materials | Pipe Hangers | Home Depot | 90 | 115 | -25
2026-02-23 | Labor | Tech Assistant | Jane Doe | 300 | 320 | -20
2026-02-24 | Materials | Condenser Unit | Lennox | 5000 | 4800 | 200
2026-02-25 | Materials | Line Set | Ferguson HVAC | 400 | 390 | 10
2026-02-26 | Labor | HVAC Tech | Robert Smith | 950 | 850 | 100
2026-02-27 | Materials | Solder & Flux | Home Depot | 100 | 85 | 15
2026-02-28 | Materials | Duct Tape (Professional) | Lowe's | 80 | 55 | 25
2026-03-01 | Subcontract | Concrete Pad Pour | Cement LLC | 1400 | 1350 | 50
2026-03-02 | Materials | P-Traps | Ferguson Plumbing | 120 | 140 | -20
2026-03-03 | Labor | Lead Tech | John Doe | 677 | 600 | 77
2026-03-04 | Materials | Electrical Breakers | Home Depot | 150 | 190 | -40
2026-03-05 | Materials | Thermostat Wire | Lowe's | 80 | 110 | -30
2026-03-06 | Labor | HVAC Tech | Robert Smith | 899 | 800 | 99
2026-03-07 | Materials | Furnace Filter Rack | Lennox | 250 | 250 | 0
2026-03-08 | Equipment | Scaffolding Rental | Sunbelt Rentals | 400 | 450 | -50
2026-03-09 | Materials | Pipe Insulation | Ferguson Plumbing | 300 | 230 | 70
2026-03-10 | Labor | Plumber Assistant | Sam Lee | 350 | 350 | 0
2026-03-11 | Materials | Caulking Guns/Tubes | Home Depot | 50 | 70 | -20
2026-03-12 | Materials | Condensate Pump | Ferguson HVAC | 180 | 210 | -30
2026-03-13 | Labor | Lead Tech | John Doe | 600 | 600 | 0
2026-03-14 | Materials | Braze Rods | Lowe's | 90 | 115 | -25
2026-03-15 | Subcontract | Crane Service (Roof) | Lift Co | 2500 | 2400 | 100
2026-03-16 | Materials | Rooftop Curbs | Lennox | 800 | 850 | -50
2026-03-17 | Labor | HVAC Tech | Robert Smith | 800 | 800 | 0
2026-03-18 | Materials | Flashing/Roof Sealant | Home Depot | 198 | 160 | 38
2026-03-19 | Materials | Angle Iron | Lowe's | 300 | 240 | 60
2026-03-20 | Labor | Tech Assistant | Jane Doe | 310 | 300 | 10
2026-03-21 | Materials | Gas Shutoff Valves | Ferguson Plumbing | 200 | 185 | 15
2026-03-22 | Materials | Flex Gas Line | Home Depot | 150 | 135 | 15
2026-03-23 | Labor | Lead Tech | John Doe | 600 | 600 | 0
2026-03-24 | Materials | Sheet Metal Plenum | Custom Metal Inc | 1500 | 1400 | 100
2026-03-25 | Materials | Canvas Connectors | Ferguson HVAC | 180 | 210 | -30
2026-03-26 | Labor | HVAC Tech | Robert Smith | 800 | 800 | 0
2026-03-27 | Materials | Hardware (Bolts/Nuts) | Grainger | 150 | 195 | -45
2026-03-28 | Materials | Motor Capacitor | Lennox | 60 | 85 | -25
2026-03-29 | Subcontract | Flooring Repair | Wood Specialists | 1700 | 1600 | 100
2026-03-30 | Materials | Grout & Tile Patch | Home Depot | 200 | 260 | -60
2026-03-31 | Labor | Lead Tech | John Doe | 600 | 600 | 0
2026-04-01 | Materials | Wall Plates | Lowe's | 40 | 65 | -25
2026-04-02 | Labor | Final Cleanup Crew | Labor Ready | 500 | 450 | 50
2026-04-03 | Materials | Touch-up Paint | Sherwin Williams | 120 | 145 | -25
2026-04-04 | Equipment | Dehumidifier Rental | Sunbelt Rentals | 300 | 350 | -50
2026-04-05 | Materials | Air Vent Filters | Home Depot | 100 | 115 | -15
2026-04-06 | Labor | Admin/Billing Time | Key Forecasts | 500 | 500 | 0
2026-04-07 | Materials | Warranty Stickers | Vistaprint | 50 | 75 | -25
2026-04-08 | Labor | QA/QC Walkthrough | John Doe | 400 | 400 | 0
2026-04-09 | Materials | Final Pipe Wrap | Ferguson Plumbing | 100 | 135 | -35
2026-04-10 | Permits | Closeout Certificate | City of Los Angeles | 150 | 150 | 0
2026-04-11 | Materials | Client Care Kit | Amazon | 80 | 95 | -15
2026-04-12 | Labor | Closeout Lead | John Doe | 300 | 300 | 0

## BLANK Data Job Costing Tracker
| Key Forecasts |  | CONSTRUCTION COMPANY ABC
| info@keyforecasts.com |  | JOB COSTING REPORT
| Phone: 213-444-2224 |  | January 1 - May 30, 2026
Date | Category | Description | Vendor/Employee | Budgeted | Actual | Variance | Metric | Results | Progress Bar | Estimate Used
2026-02-10 | Materials | Copper Piping | Home Depot | 3 | 1 | 2 | Total Contract Price | 4 |  | 33.33%
[6 empty] | 0 | Total Estimated Costs | 3
[6 empty] | 0 | Total Actual Costs | 1
[6 empty] | 0 | Gross Profit (Actual) | 3
[6 empty] | 0 | Net Profit Margin % | 75%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Instructions
Tutorial: Construction Job Costing Report
This tutorial will guide you through using this Excel workbook to track your project profitability in real-time.
This tool is designed to help you identify cost slippage immediately so you can protect your bottom line.
1. Setting Up Your Project Information
At the top of the sheet, you have full control over the branding and project headers. You can click directly into these cells to update:
Company Branding: Update the name, email (info@keyforecasts.com), and phone number (213-444-2224) to reflect your specific business.
Report Details: Change the "CONSTRUCTION COMPANY ABC" and "JOB COSTING REPORT" titles to your specific client or project name.
Reporting Period: Update the date range to match your project timeline.
2. Allocating Your Budget (The Yellow Area)
The yellow-highlighted cell (Total Contract Price) is the most critical starting point.
How to use it: Enter the total amount you are billing the client for the entire project here.
Why it matters: This figure is the "top line" revenue that all your profit margins and
percentages are calculated against. If the contract price changes due to a change order, update this cell immediately to keep your metrics accurate.
3. Recording Project Expenses (The Data Table)
The main body of the sheet is where you track every dollar spent. Use the columns as follows:
Date: Enter the date the expense occurred or the invoice was received.
Category: Use this to group costs (e.g., Labor, Materials, Permits, Subcontract).
Description: Provide a brief note about the specific expense (e.g., "Rough-in Copper Piping").
Vendor/Employee: Track who was paid, whether it's a supplier like "Home Depot" or an employee like "John Doe."
Budgeted: Enter the amount you estimated for this specific line item during the bidding phase.
Actual: Enter the exact amount you ended up paying.
IMPORTANT: Do not touch the Variance column. This column contains a built-in formula that automatically
calculates the difference between your Budgeted and Actual amounts. It will highlight in red if you are over budget, providing an instant visual warning.
4. Understanding Your Metrics
The Metric table provides a high-level financial health check of your project:
Metric | Meaning
Total Contract Price | The total revenue expected from the client.
Total Estimated Costs | The sum of all "Budgeted" amounts in your data table.
Total Actual Costs | The sum of all "Actual" amounts paid out to date.
Gross Profit (Actual) | Your take-home pay after all expenses (Contract Price minus Actual Costs).
Net Profit Margin % | Your efficiency rating. It shows what percentage of every dollar earned is kept as profit.
5. The Visual Dashboard
Progress Bar: This bar fills up automatically based on your spending.
Estimate Used: This percentage shows how much of your total project budget has been "burned."
In the example shown, 92.13% of the estimate has been used. If this number approaches 100%
before the project is finished, it’s time to review your costs.
If you have questions, please send an email to info@keyforecasts.com